## Summary
Phase-Exit Review
Organisation / Department: | UPF Gestió de projectes
Project Name: | EPEAK
Project Owner: | Elena Díaz
Project Core Team Number: | 102.G
Project Core Team members: | Elena Barrio, Judit Viladecans, Paula Ceprián, Eric Berenguer, Telmo Maximlian Linacisoro
Reviewer Name: | Miquel Oliver
Overall Compliance (%) | 71.84%
Overall Phase-Exit Status: | 0.71842
Area | Phase-Exit Status | % of Phase Compliance | Date | Already performed?
Initiating | 100% | 100% | 2024-10-06 | Yes
Planning | 90% | 90% | 2024-10-20 | Yes
Executing | 97.37% | 97.37% | 2024-12-01 | Yes
Closing | 0% | 0% | dd/mm/yyyy | No
Assessment Key:
0.3 | Major key activities for the phase(s) weren't performed (50% of the key activities or more are still to be completed).
0.7 | Some key activities are still to be completed before the phase(s) can be closed (% of compliance between 51% and 80%).
0.9 | Nearly all the key activities for the phase(s) are complete (more than 80% of the key activities). The decision to move to another phase should be taken considering the relevance / adequacy of the remaining activities to the project and its specificities.
Yes
No

## Initiating
| Initiating Phase-Exit Checks |  | Date: | 2024-10-06
% of Phase Compliance |  |  | 100% | 100%
# | Description | Answer | Score | Comments
1 | Has a Project Initiation Request been documented and approved? | Yes | 10 | It has been approved
2 | Are the project context, scope, deliverables and expected outcomes documented? | Yes | 10
3 | Has a Project Owner (PO) been identified? | Yes | 10 | Elena Díaz
4 | Has the project theme been agreed with the challenge mentor? | Yes | 10
5 | Are success criteria documented? | Yes | 10 |  | Yes
6 | Are the success criteria SMART? | Yes | 10 |  | Yes, Partially
7 | Have all the key project stakeholders been identified? | Yes | 10 |  | No
8 | Are all the initial roles and responsibilities defined? | Yes | 10 |  | N/A
9 | Are major assumptions and constraints identified? | Yes | 10
10 | Have the major risks been identified? | Yes | 10
11 | Is there a Project Manager (PM) assigned to the project? | Yes | 10
12 | Has the PCT decided whether to change the Project Manager (PM) rol? | Yes | 10 | We have decided not to change it
13 | Has a Project Charter been documented by the Project Core Team (PCT)? | Yes | 10
14 | Has a Project Charter video link been delivered? | Yes | 10
15 | Has the Project Charter been approved by the Power Steering Commitee (PSC)? | Yes | 10
16 | Have all deliverables been placed in the project repository Google Drive? | Yes | 10
17 | Have all deliverables followed the configuration plan? | Yes | 10
18 | Is the project ready to proceed to the Planning Phase? | Yes | 10
| Total score for compliance | 0 | 180

## Planning
| Planning Phase-Exit Checks |  | Date: | 2024-10-20
% of Phase Compliance |  |  | 90% | 90%
# | Description | Answer | Score | Comments
1 | Is the Stakeholder Matrix complete with all the relevant stakeholders' names and contact details? | Yes | 10
2 | Are all project roles and responsibilities detailed? | Yes | 10
3 | Is the project scope broken-down in manageable components that allow accurate estimation of resources, work effort and duration? | Yes | 10 |  | Yes
4 | Is the project work breakdown structure completed ? | Yes | 10 |  | Yes, Partially
5 | Has the product scope been agreed with the challenge expert or mentor? | Yes | 10
6 | Is the Project Work Plan baselined and approved by the Project Steering Committee (PSC)? | Yes | 10 |  | N/A
7 | Are all the communication items (e.g. meetings and reports) defined as well as their frequency? | Yes | 10
8 | Is a Risk Management Plan documented as a separate document? | Yes | 10
9 | Has a configuration management procedure been documented? | Yes | 10
10 | Is there a Project Handbook documented? | Yes | 10
11 | Are all the major deviations from the Project Charter approved by the Project Steering Committee (PSC)? | Yes | 10
12 | Is the project currently delivering to schedule? | Yes | 10
13 | Are all resources available for the executing phase? | Yes | 10
14 | Is the project currently delivering to schedule? | Yes | 10
15 | Are all resources available for the executing phase? | Yes | 10
16 | Have all deliverables been placed in the project repository Google Drive? | Yes | 10
17 | Have all deliverables followed the configuration plan? | Yes | 10
18 | Is the project ready to proceed to the Executing Phase? | Yes | 10
| Total score for compliance | 0 | 180

## Executing
| Executing Phase-Exit Checks |  | Date: | 2024-12-01
% of Phase Compliance |  |  | 97.37% | 97.37%
# | Description | Answer | Score | Comments
1 | Have user stories and/or deliverables been performed as defined and scheduled in the work breakdown structure? | Yes | 10 |  | Yes
2 | Were artefacts produced, updated and revised as planned? | Yes | 10 |  | Yes, Partially
3 | Was the work breakdown structure refined at each sprint? | Yes | 10
4 | Was the iteration work defined at the beggining of each iteration? | Yes | 10
5 | Were the quality assurance and control activities performed as planned? | Yes | 10 |  | No
6 | Are all major risks mitigated? | Yes | 10 |  | N/A
7 | Have the products deliverables been agreed with the challenge expert or mentor? | Yes | 10
8 | Have all the approved changes been implemented? | Yes | 10
9 | Are deliverables in line with requestor needs and expectations? | Yes | 10
10 | Are all the project issues and corrective actions resolved / closed? | Yes | 10
11 | Are all product deliverables ready to be approved by the Project Owner (PO)? | Yes | 10
12 | Are all project artifacts ready to be approved by the Solution Provider (SP)? | Yes | 10
13 | Were the relevant stakeholders informed about the delivery of projects outputs? | Yes | 10
14 | Were project performance indicators and metrics captured and assessed? | Yes, Partially | 5 | We have assessed the performance of all developed models by looking at the results and comparing it to previous historical values.
15 | Have all the communication items (meetings, reports,…) been implemented as planned? | Yes | 10
16 | Did a Executing Kick-Off Meeting take place? | Yes | 10
17 | Have all deliverables been placed in the project repository Google Drive? | Yes | 10
18 | Have all deliverables followed the configuration plan? | Yes | 10
19 | Is the project ready to proceed to the Closing Phase? | Yes | 10
| Total score for compliance | 0 | 185

## Closing
| Closing Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Did a Project-End Review Meeting take place? | No | 0 | <Add here the justification for the answer given.>
2 | Has the product backlog been completed? | No | 0
3 | Did the Appropriate Governance Board (AGB) formally approve deliverables (Challenge Final Report)? | No | 0
4 | Were final project performance indicators and metrics assessed and compared to project baselines? | No | 0 |  | Yes
5 | Are project benefits and unachieved goals assessed and remaining benefits forecasted? | No | 0 |  | Yes, Partially
6 | Was client / requestor satisfaction assessed? | No | 0 |  | No
7 | In case some risks or issues couldn't be closed, are they re-assessed and follow-up actions recommended? | No | 0 |  | N/A
8 | Did all the relevant stakeholders give feedback on the overall project experience? | No | 0
9 | Were lessons learned and post-project recommendations captured? | No | 0
10 | Is the Project-End Report documented and delivered to the relevant stakeholders? | No | 0
11 | Have all deliverables been placed in the project repository Google Drive? | No | 0
12 | Have all deliverables followed the configuration plan? | No | 0
13 | Was the project formally accepted by the Project Steering Commitee (PSC), project-end report? | No | 0
14 | Have project team members performance been assessed? | No | 0
15 | Is the project ready to be closed? | No | 0
| Total score for compliance | 0 | 0